OFFSHORE ASSOCIATED GAS PROCESSING AND MONETISATION INFRASTRUCTURE IN NAMIBIA

Executive Summary:

Namibia's Orange Basin holds world-class oil and gas resources, but no field is yet at Final Investment Decision (FID). Associated gas monetization is technically feasible but commercially constrained by ultra-deepwater costs, high gas-to-oil ratios, and the absence of any existing offshore gas infrastructure. The only near-term certainty is gas reinjection at Venus; all export pathways remain speculative pending FID.

1. CONFIRMED RESOURCE BASE & OPERATOR LANDSCAPE

1.1 Verified Field Inventory

| Field / Asset | Block | Operator & Equity (Current) | Water Depth | Status | First Oil Target |
| --- | --- | --- | --- | --- | --- |
| Venus | PEL 56 (2913B) | TotalEnergies 35.25%, QatarEnergy 35.25%, Galp 10%, NAMCOR 10%, Impact 9.5% | ~3,000 m | Appraisal ongoing; FID targeted Q4 2026 | ~2029–2030 |
| Mopane | PEL 83 (2813B) | TotalEnergies 40% (op), Galp 40%, NAMCOR 10%, Custos 10% | ~1,800 m | Appraisal ongoing; TotalEnergies took operatorship Dec 2025 | 2031+ |
| Graff / Jonker / La Rona / Lesedi | PEL 39 (2913A/2914A) | Shell 45% (op), QatarEnergy 45%, NAMCOR 10% | ~2,000–2,700 m | Impaired. Shell wrote down $400M in Jan 2025; Graff/Jonker deemed commercially unviable due to low permeability and high GOR. New exploration (Merlin-1X, 2026) ongoing. | Indefinite |
| Kudu | 2814A | BW Energy 95%, NAMCOR 5% | 170 m | Appraisal complete (Kharas-1, 2025); FID targeted late 2026 | 2028–2029 |
| Other | PEL 85, 90, etc. | Chevron, Rhino Resources, Petrobras, Woodside | 1,500–2,500 m | Early exploration | 2032+ |

TotalEnergies became operator of Mopane in December 2025 after acquiring a 40% interest from Galp, consolidating control over Namibia's two largest offshore discoveries.

1.2 Resource Classification: In-Place vs. Recoverable

The original document conflated oil-in-place with recoverable reserves. This is a material distinction for investment decisions.

| Field | Oil In-Place (Est.) | Recoverable Oil/Condensate (Est.) | Associated Gas (Est.) | Confidence |
| --- | --- | --- | --- | --- |
| Venus | ~5.1 billion barrels | ~750 million barrels | 5–8 Tcf (associated, in-place) | Moderate–High |
| Mopane | ~10 billion boe in-place | ~2 billion boe recoverable | 3–5 Tcf (associated, contingent) | Moderate |
| Graff | — | ~200 million barrels (impaired) | High GOR; not commercially viable as configured | Low |
| Jonker | — | ~300 million barrels (impaired) | High GOR; not commercially viable as configured | Low |
| Kudu | — | 1.3 Tcf gas (2C contingent); 755–2,308 Bscf range | Non-associated (dry gas + new condensate/light oil at Kharas-1) | Moderate |

2. ASSOCIATED GAS PROCESSING: TECHNICAL REALITY

2.1 The Core Constraint

Ultra-deepwater FPSOs (1,800–3,000 m) face severe weight, power, and footprint limits. Venus's associated gas production is estimated at 800–1,200 scf/bbl, requiring massive reinjection or processing capacity. TotalEnergies has publicly confirmed that gas reinjection is the favored near-term solution for Venus, noting that reinjection at 3,000 m water depth has never been attempted at this scale.

2.2 Processing Train Requirements (Confirmed)

If export infrastructure is built, the following processing chain is technically standard for Orange Basin gas:

- Subsea gathering & separation (10,000–15,000 psi rated trees; 15–30 km tie-backs)

- Multi-stage separation (HP/MP/LP flash vessels)

- Gas compression (electric-drive centrifugal; 45–60 MW demand per 180 kbpd FPSO)

- Dehydration (TEG or molecular sieve to <0.1 ppm water)

- Acid gas removal (MDEA/DEA for CO₂ at 1.0–2.5% mol; mercury removal beds)

- Hydrocarbon dew-point control (JT valves or turbo-expanders for C₃+ extraction)

- Condensate/LPG handling (spiked to crude or routed to fractionation)

- Reinjection compression (350–500 bar for reservoir pressure support)

2.3 Gas Quality Specifications by End-Use

| Parameter | Reinjection | Pipeline to Shore | FLNG Liquefaction | Domestic Industry |
| --- | --- | --- | --- | --- |
| CO₂ | <5% mol | <2% mol | <50 ppm | <2% mol |
| H₂S | <100 ppm | <10 ppm | <4 ppm | <10 ppm |
| Water dew point | <-10°C | <-8°C @ 100 bar | <-100°C (0.1 ppm) | <-8°C @ 70 bar |
| Operating pressure | 350–500 bar | 120–180 bar | 50–70 bar | 40–70 bar |

3. MONETIZATION PATHWAYS: CERTAINTY RANKING

| Rank | Pathway | Certainty | Rationale |
| --- | --- | --- | --- |
| 1 | Gas Reinjection (Venus) | High | Required for First Oil (~2029–2030). No export infrastructure will be ready in time. TotalEnergies has confirmed this approach. |
| 2 | Kudu Gas-to-Power | Moderate | FID targeted late 2026. 400–420 MW initial phase, expandable to ~800 MW. BW Energy 95%, NAMCOR 5%. Kharas-1 discovery of liquids improves economics. |
| 3 | LPG / NGL Extraction | Low–Moderate | Technically feasible but requires dedicated fractionation infrastructure not yet planned. |
| 4 | Pipeline to South Africa | Low | No FID. Requires >70% utilization to achieve viable tariffs ($1.20–1.80/MMBtu). No confirmed anchor off-taker. |
| 5 | FLNG Export | Low | Conceptually attractive but capital intensive ($3.5–6.0B per unit). No operator has announced FLNG FEED. Requires steady 130 MMscfd per 1.0 Mtpa train. |

Judgment: For the period 2028–2032, the only bankable gas monetization is reinjection at Venus and Kudu domestic power. All other pathways are strategic options, not committed projects.

4. INFRASTRUCTURE & INVESTMENT: INDICATIVE ESTIMATES

| Infrastructure Segment | Indicative Capacity | Indicative CAPEX | Timeline | Status |
| --- | --- | --- | --- | --- |
| FPSO Gas Topsides (3 units) | 750 MMscfd combined | $1.2–1.6B | 2026–2030 | Conceptual; Venus FPSO only one with defined schedule |
| Deepwater Subsea Gathering Hub | 24-inch, 60 km | $0.8–1.1B | 2028–2030 | Not sanctioned |
| Offshore Trunkline to Shore | 20-inch, 180 km | $1.4–1.9B | 2028–2031 | Not sanctioned |
| Onshore Gas Terminal (Lüderitz) | 500 MMscfd | $0.6–0.8B | 2029–2031 | Not sanctioned |
| Kudu CCGT (Oranjemund) | 400–800 MW | $1.0–1.4B | 2026–2029 | Under development; FID late 2026 |
| Lüderitz CCGT Expansion | 500 MW | $0.6–0.8B | 2030–2032 | Conceptual |
| LPG Extraction & Fractionation | 250,000 t/yr | $0.3–0.5B | 2029–2031 | Conceptual |
| FLNG Unit | 3.5 Mtpa | $3.8–4.8B | 2031–2035 | Conceptual |
| NamPower Grid Upgrades (400kV) | 1,500 MW export | $0.9–1.2B | 2027–2031 | Planned |
| Port of Lüderitz Expansion | Berthing & logistics | $0.5–0.8B | 2026–2030 | Under construction (N$4B) |

5. DOMESTIC MARKET REALITY CHECK

5.1 Verified Domestic Demand (Post-FID Scenarios)

| Sector | Demand (MMscfd) | Certainty |
| --- | --- | --- |
| Power (Kudu + Orange Basin CCGT) | 150–250 | Moderate (Kudu FID pending) |
| Mining & smelting | 40–70 | Low (requires pipeline infrastructure) |
| Fertilizer & chemicals | 50–90 | Low (no projects at FEED) |
| LPG / household | 15–25 | Moderate (can absorb Kudu NGLs) |

Peak domestic demand: ~320–420 MMscfd by 2035–2040.

5.2 Supply-Demand Balance

| Year | Offshore Gas Supply (Est.) | Reinjection Demand | Net Available | Domestic Demand | Exportable Surplus |
| --- | --- | --- | --- | --- | --- |
| 2028 | 100 | 80 | 20 | 0 | 20 (Kudu only) |
| 2030 | 450 | 300 | 150 | 120 | 30 |
| 2032 | 950 | 450 | 500 | 220 | 280 |
| 2035 | 1,400 | 550 | 850 | 320 | 530 |
| 2040 | 1,800 | 600 | 1,200 | 420 | 780 |

If all projects reach plateau, domestic demand alone cannot absorb total associated gas. A dual-track strategy (domestic power + export) is logically necessary, but export infrastructure is not yet financeable.

6. RISK ASSESSMENT & STRATEGIC SCENARIOS

6.1 Critical Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Venus FID delay beyond 2026 | Moderate | High | TotalEnergies has stated $20/bbl cost ceiling; government cost-sharing talks ongoing |
| Shell PEL 39 failure to find viable development | Moderate | Moderate | Merlin-1X (2026) is promising but not a development; Shell may exit or farm down |
| Kudu FID delay | Moderate | High | Already delayed from 2024→2025→late 2026; liquids discovery improves case |
| Gas reinjection technical failure at 3,000 m | Low–Moderate | Very High | No global precedent; requires bespoke subsea compression |
| Domestic offtaker credit risk | Moderate | Moderate | NamPower financial health; SAPP pricing uncertainty |

6.2 Three Scenarios for Decision-Makers

| Parameter | Scenario A: Conservative (Reinjection-Only) | Scenario B: Balanced (Domestic Anchor) | Scenario C: Integrated Export Hub |
| --- | --- | --- | --- |
| 2035 Gas Production | 1,200 MMscfd | 1,400 MMscfd | 1,800 MMscfd |
| Reinjection Share | 85% | 40% | 30% |
| Domestic Market Share | 15% | 55% | 25% |
| Export Share | 0% | 5% | 45% |
| Program CAPEX (indicative) | $2–3B | $6–8B | $16–18B |
| Namibia Power Self-Sufficiency | Unchanged (~45% import) | 100% self-sufficient | Net exporter |
| Cumulative State Revenue (indicative) | $2–3B | $6–8B | $15–20B |
| Strategic Fit | Sub-optimal | Most Probable | Aspirational |

Judgment: Scenario B is the most realistic through 2035. Scenario C requires simultaneous FIDs on FLNG and a regional pipeline—an unlikely capital stack given current operator caution.

7. DECISION POINTS & RECOMMENDATIONS

Immediate Actions (0–12 Months)

- Correct the regulatory baseline. Namibia lacks a published Associated Gas Utilization Policy. Decision-makers should demand clarity on:

  - Flaring restrictions and reinjection rights

  - Gas ownership split between oil and gas phases

  - Third-party access to common infrastructure

- Secure Kudu FID. This is the only project with a credible path to first gas before 2030. Delay beyond late 2026 would push Namibia's energy independence timeline to the mid-2030s.

- Update equity registers. All government briefings must reflect the Dec 2025 TotalEnergies–Galp swap. Outdated ownership tables damage credibility in investor discussions.

Medium-Term Actions (1–3 Years)

- Mandate gas-gathering readiness on all FPSOs. Even if reinjection is Phase 1, FPSO topsides should be designed for future tie-in to a shared trunkline.

- Establish a Common-User Infrastructure SPV. A NAMCOR-led special purpose vehicle for the Orange Basin trunkline would de-risk individual operator investments and standardize tariffs.

- Commission a bankable domestic demand study. The 320–420 MMscfd domestic demand figure is analytical, not contracted. Secure PPAs with NamPower, mining houses, and industrial users before pipeline FEED.

Long-Term Positioning (3–7 Years)

- Preserve FLNG optionality. Do not commit to FLNG FEED until Venus and Mopane have 3–5 years of production data confirming sustained gas volumes and composition.

- Negotiate a Namibia–South Africa gas pipeline MOU. Even if not built until the 2030s, a government-level framework on tariffs, transit rights, and environmental approvals would accelerate private investment.

ANNEX: DATA CONFIDENCE MATRIX

| Section | Confidence Level | Basis |
| --- | --- | --- |
| Field discoveries & operatorship | High | Operator disclosures, regulatory filings |
| Equity percentages | High | Post-Dec 2025 swap agreements |
| Resource volumes (in-place) | Moderate | Operator estimates; not independently audited |
| Resource volumes (recoverable) | Moderate–Low | Early appraisal; subject to change |
| First oil timelines | Moderate | Contingent on FID; Venus most advanced |
| Infrastructure CAPEX | Low | Author's/industry estimates; no FEED completed |
| Domestic demand projections | Low–Moderate | Analytical modeling; no firm offtake contracts |
| Shell Graff/Jonker viability | High (negative) | Confirmed $400M impairment; commercially unviable |